ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Beneficiary country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	4

2.	ASSUMPTIONS & RISKS	4

2.1.	Assumptions underlying the project	4

2.2.	Risks	4

3.	SCOPE OF THE WORK	4

3.1.	General	4

3.2.	Specific work	5

4.	LOGISTICS AND TIMING	6

4.1.	Location	6

4.2.	Start date & Period of implementation of tasks	6

5.	REQUIREMENTS	6

5.1.	Staff	6

5.1.1	Translator	6

5.1.2	Interpreter	7

6.	REPORTS	7

6.1.	Reporting requirements	7

6.2.	Submission and approval of reports	7

7.	MONITORING AND EVALUATION	8

7.1.	Definition of indicators	8

7.2.	Special requirements	8

# BACKGROUND INFORMATION

## Beneficiary country

Republic of Macedonia

## Contracting Authority

Municipality of Bitola

## Country background

- As of 1 January 2007, the Beneficiary Country is eligible for all 5 components of the Instrument for Pre - Accession Assistance. In the frame of the Instrument for pre-accession assistance (IPA) and its second Component for Cross-border Cooperation, Macedonia is implementing the cross-border programme with Greece in the period of 2007-2013.

- The IPA Cross-Border Cooperation Programme Greece - Republic of Macedonia (hereinafter: CBC Programme) was adopted for the Programming Period 2007-2013 and intends to ensure a better co-ordination of programmes and activities among Greece as a Member State and the Republic of Macedonia as a neighbouring candidate country. Its Global Objective is to promote and protect the environmental resources of the area. The programme has two priorities, and the second one is the enhance  the environmental resources and cultural heritage of the programme area. The main objective of the project is The strategic objective of the project is to protect the environment and its resources, promote the conformity with the European Union and the national energy targets for 2020 and contribute to the global effort to confront the climate change.

- The Pelagonia Region of Republic of Macedonia is among eligible Programme regions, where the Contracting Authority, Municipality of Bitola is located and carries out the regular activities.

## Current situation in the sector

With Decision of the Joint Steering Committee, the project proposal “,,Protection of the environment through the promotion of biomass for substitution of fossil fuels in heating and power generation/Biofoss,,was approved for financing from the Programme funds. The Grant Contract for EU funding of the project was signed between the Delegation of EU and the Municipality of Bitola under CRIS No. IPA/2010/DN023658/CN359693 from 14 July 2015.

Heating and power generation in the cross border area are heavily based on fossil fuels. Besides the industrial grade power generation of electricity based on lignite in both sides of the boarders, lignite is also heavily used for space heating purposed. Indeed, an operational district heating network in Amyntaio municipality managed by DETEPA and one that is in the design stage in Bitola are based on lignite as they are utilizing or planning to utilize the redundant heat of the lignite power stations in the area. Moreover a large number of mainly rural households use lignite for heating purposes, and due to the financial crisis lignite and fire woods are displacing heating oil also in urban areas. Furthermore a lot of municipalities around EU  have successfully introduced biomass as an alternative to fossil fuels for both centralized district heating systems and small scale household use. The intense agricultural activity in the cross border area  provides an abundance off different types of biomass according to national statistical authorities. types of biomass according to national statistical authorities. The core idea behind the project is to extent the knowledge of the region regarding the utilization of biomass as a source of clean energy. Moreover to study biomass technologies for heat or CHP production for district heating and demonstrate through pilot projects, dissemination activities and study visits on EU region where biomass is widely utilized.

Environment, Energy and Quality of life are firmly tied. Level of life is not adequate when environment is degraded and energy is missing or used irrationally. For satisfying the strategic and the specific objectives of the ETC Programme the proposed plan addresses the following opportunities for the cross-border area:

- EU focus on environmental protection policies including a trans boundary dimension, and

- promotion of the natural heritage.

Furthermore, this project helps in the elimination of current weaknesses in the cross-border area, which are:

- Co-operation in the field of environmental protection which is still weak,

- no common plan and actions on environmental protection, and

- lack of management plans for protected areas in the non-Member States.

Last but not least, the implementation of such a project will highly help the participating municipalities to benefit from their strengths:

- Protection of natural environment and valuable ecosystems,

- Protection of the rich natural heritage and developed environmental institutions, and

- Networks exchanges reinforced during the past cross-border experience.

Besides the above more general threats and opportunities the cross border region have to confront the following local threats and take advantage of the following local opportunities:

Threats:

The lignite thermoelectric power plant operating in the regions and providing heat for the district heating networks (under planning in Bitola, and operational in Amyntaio) are rather outdated and there is a threat of stop operating in the near future; thus a more sustainable and not polluting alternative energy source like biomass must be considered in the strategic energy planning

Opportunities:

Agricultural activity and economy in the region can be reinforced by utilizing its by products as an energy resource.

The high prices of heating oil can be seen as an opportunity to reinvent household energy generation and consumption and to prevent the attitude of rolling back to old-fashioned heating solutions.

The target groups addressed by the current project include: the municipalities and the municipal enterprises, the education and research institutions and centres, the regional planning authorities, the energy and the construction sector, as well as the wider society.

Biofoss by its conceptual development is a very logical project, with actions deriving from previous ones and leading to the following logical steps. However, as projects always face some ever changing situations, the partners have agreed to establish a Coordinating body bringing together the Technical Services of DETEPA and the Municipality of Bitola, as well as the scientific staff from TEI. This body will communicate on a constant basis through telephone, skype, emails, etc, in order to secure the smooth implementation of the project. Above this body, the Steering Committee, formed by the representatives of the three partners, will provide guidance and ultimate solutions to those issues that remain unsolved. All this work is part of the WP1, along with the production of all necessary Reports (progress, Final, etc). This WP lasts for the entire duration of the project (15 months)

WP2 targets Information and Publicity as of a great importance for the project , including the organization of two Conferences (kick off and Final), three Workshops related to Biomass availability, Energy Efficiency and Cluster and economic development. After the development of a detailed communication plan, the tools applied will include the project’s web site, the production of promotion material (brochures, leaflets, flash drives and CD ROM, newsletters), while the promotion campaign strategy includes articles and announcements in local newspapers, TV spots, promotion through social media, etc. WP3 focuses on the identification of biomass availability - quality and cost- supply chain in the cross border area,  and determining the potential biomass technologies for heat or CHP production for DH, ending up with a relevant workshop .

WP4 targets the identification of local buildings energy efficiency, by measuring a sample of them and statistically projecting to the entire building population. The results will be presented and discussed during an appropriate workshop. WP5 attempts to bridge the offer and demand sides, by bringing them together into a Cluster and by analyzing the potential of covering the heat demand of local buildings with biomass units. Finally, WP6 demonstrates in practice all the above: the pilot installation of two units with pellet lines in selected buildings will provide evidence of its viability to the local and regional stakeholders as well as to the wider society, while it will raise awareness of local farmers for the potential of developing sustainable local fuels for local needs.

## Related programmes and other donor activities

N/A

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Constant and timely support from the Project team;

- Good co-operation between Contracting Authority and selected Contractor;

## Risks

- Failure to comply with the respective deadlines for completion and launching of the tender procedures;

# SCOPE OF THE WORK

## General

### Description of the assignment

The assignment of the present contract is to provide:

Translation

- Translation from Macedonian to English or from English to Macedonian for text 20 pages A4 format from the project activities that will be organized during project implementation. There will be translated materials from 3 workshops, 2 conferences, 1 study visit, 1 installation of the biomass boiler and mini pellet line.

For translation activities, translator will receive the text materials from Municipality of Bitola separately from each event during implementation of the project. Translation of text materials for each event should be finished 48 hours after receiving the text material. Text materials will be sent to translator electronically version by e-mail or printed by post.

Interpreting

- Interpreting from English to Macedonian for the needs on the Workshop about Biomass availability and quality in the region that will be organized in Greece

- Interpreting from English to Macedonian and from Macedonian to English for the needs on the Workshop for the role of biomass in space heating in the cross border region that will be organized in Bitola

- Interpreting from English to Macedonian and from Macedonian to English for the needs on the Workshop for the role of biomass and biomass clusters for the overall economic development in the cross border region that will be organized in Greece

- Interpreting from English to Macedonian and from Macedonian to English for the needs on the Kick off Conference that will be organized in Greece

- Interpreting from English to Macedonian and from Macedonian to English for the needs on the Closing Conference that will be organized in Bitola (for this conference there will be 2 interpreters)

For interpreting activities, interpreter will be informed minimum 1 day before the event and will receive agenda about the event. After each event interpreter should prepare short report about  the event. Report for each event should be finished 7 days after the event. Reports will be sent to Municipality of Bitola electronically version by e-mail and printed by post.

### Geographical area to be covered

Municipality of Bitola - Republic of Macedonia, Municipality of Amyntaio, Municipality of Kozani- Republic of Greece

## Specific work

Translation

- Translation from Macedonian to English or from English to Macedonian for text 20 pages A4 format from the project activities that will be organized during project implementation. There will be translated materials from 3 workshops, 2 conferences, 1 study visit, 1 installation of the biomass boiler and mini pellet line.

For translation activities, translator will receive the text materials from Municipality of Bitola separately from each event during implementation of the project. Translation of text materials for each event should be finished 72 hours after receiving the text material. Text materials will be sent to translator electronically version by e-mail or printed by post.

Interpreting

- Interpreting from English to Macedonian and from Macedonian to English for the needs on the Workshop about Biomass availability and quality in the region that will be organized in Greece

- Interpreting from  English to Macedonian and from Macedonian to English for the needs on the Workshop for the role of biomass in space heating in the cross border region that will be organized in Bitola

- Interpreting from English to Macedonian and from Macedonian to English for the needs on the Workshop for the role of biomass and biomass clusters for the overall economic development in the cross border region that will be organized in Greece

- Interpreting from English to Macedonian and from Macedonian to English for the needs on the Kick off Conference that will be organized in Greece

- Interpreting from English to Macedonian and from Macedonian to English for the needs on the Closing Conference that will be organized in Bitola (for this conference there will be 2 interpreters)

For interpreting activities, interpreter will be informed minimum 1 day before the event and will receive agenda about the event. After each event interpreter should prepare short report about  the event. Report for each event should be finished 48 hours after the event. Reports will be sent to Municipality of Bitola electronically version by e-mail and printed by post.

### Responsible body

Municipality of Bitola, Republic of Macedonia

The Contractor shall report to the relevant representative appointed by the Municipality of Bitola.

### Facilities to be provided by the Contracting Authority and/or other parties

N/A

# LOGISTICS AND TIMING

## Location

The operational base for the project will be set up in the town of Bitola, Republic of Macedonia.

## Start date & Period of implementation of tasks

The intended start date is 14.12.2015 and the period of implementation of the contract will be not late than  14.10.2016 .

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the beneficiary country cannot be proposed as a translator or interpreters, unless prior written approval has been obtained from the European Commission.

Statements of Exclusivity and Availability are necessary for the translator and interpreters:

This Terms of Reference contains translator and interpreters profiles and the tenderer shall submit CVs and Statement of Exclusivity and Availability for the translator and interpreters.

### Translator

Qualifications and skills

- University's degree or Certificate of duty enrolments ;

General professional experience

- At least 3 years professional experience in fields related to this contract. (Contracts or invoices for implemented activity related to the contract)

Specific professional experience

- Experience  in translation from Macedonian to English e.t.c in the past 3 years (Contracts or invoices for implemented activity related to the contract)

- Recommendations

Translator must be independent and free from conflicts of interest in the responsibilities they take on.

### Interpreters

Qualifications and skills

- University's degree;

- Certificate of duty enrolments;

General professional experience

- At least 3 years professional experience in fields related to this contract. (Contracts or invoices for implemented activity related to the contract)

Specific professional experience

- Experience  in interpreting from Macedonian to English e.t.c in the past 3 years (Contracts or invoices for implemented activity related to the contract)

- Recommendations

Interpreters must be independent and free from conflicts of interest in the responsibilities they take on.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original:

- Report for translation – It shall be submitted to the address of the Contracting Authority specified in the Instruction to Tenderers no later than 3 days before the end of the period of implementation of tasks. The report shall contain a sufficiently detailed description of the implemented activities through the contract implementation. The final report must be provided along with the corresponding invoice relating to the balance payment of the contract as well as a delivery acceptance sheet.

- Report for interpretation – It shall be submitted to the address of the Contracting Authority specified in the Instruction to Tenderers no later than 3 days before the end of the period of implementation of tasks. The report shall contain a sufficiently detailed description of the implemented activities through the contract implementation. The final report must be provided along with the corresponding invoice relating to the balance payment of the contract as well as a delivery acceptance sheet.

## Submission and approval of reports

The report referred to above must be submitted to the Municipality of Bitola Identified in the contract. The Project Management team is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

All activities for monitoring and evaluation which will be  a part   on this Contract will  be realized according the planed time and measures of progress towards expected results.

## Special requirements

N/A

IPA Council Regulation (EC) No. 1085/2006, adopted on 17 July 2006. January 10, 2010.